## Grant Summary
City-Wide Grant Opportunities
Last Updated: 04/08/25
CURRENT GRANTS
| City Department | Contact | Grant Agency | Grant Name | Purpose of the Grant | Grant Amount | City Match Required to Receive the Grant | ARPA Funded | Total Project Value | Notes | What needs done?
1 | Cultural and Civic Services | Cari Rupkalvis | FL Dept. of State, Div. of Library and Information Services | Public Library Construction Grant | Library construction project | 500000 | 500000 |  | 1000000 | Extension granted to 09/29/25/Construction underway
2 | Fire Dept. | Kyle Miller/Megan Araya | FEMA | SAFER | Hiring of personnel | 928000 | 0 |  | 928000 |  | FEMA has not reimbursed for January yet/Feb. and March not submitted
3 | Police Dept. | Frank Ruggiero/Raquel Hull | Dept. of Justice | Bulletproof Vest Grants (2024) | Grant for equipment purchase | 8390.14 | 8390.14 |  | 16780.28 | Expiration date of 08/31/26
4 | Police Department | Frank Ruggiero | FDLE | JAG-D (Direct) | Body Worn Cameras | 4717 | 0 |  | 4717 | Awarded | Reimbursement submitted
5 | Police Dept. | Steve Gassen/P.J. Harbert | FDOT | Highway Safety | DUI Enforcement/Saturation Patrols | 30000 |  |  | 30000 | Awarded | Reimbursement needs submitted
6 | Police Dept. | Anthony Boone/P.J. Harbert | IPTM | High Visibility Enforcement Grant | HVE | 5000 |  |  | 5000 | Awarded | Reimbursement submitted
7 | Police Department | Frank Ruggiero | FDOT | DRE Callout | DRE Callout | 3000 |  |  | 3000 | Awarded
8 | Project Admin | Bob Robertson | State of Florida | Budget Appropriation | Funding to support Anclote River Dredging (Spoils site lease and construction and extended turning basin) | 1400799 | 0 |  | 1400799
9 | Project Admin | Bob Robertson | Pinellas County | Budget Appropriation | Funding to support restoration of the Anclote Dredge DMMA (spoils site). | 214176 | 0 |  | 214176
10 | Project Admin | Bob Robertson | State of Florida | Budget Appropriation | Mango Street Construction, Phase 2 | 925000 | 728935 |  | 1653935
11 | Project Admin | Bob Robertson or PJ Harbert | State of Florida | Budget Appropriation | Tarpon Springs Sponge Docks Flooding Abatement Project | 4881230.52 | 0 |  | 4881230.52 | HMGP Funding: 3,142,840 State Appropriation Funding: 1,738,390 | Engineering and Environmental Review complete/waiting on direction from FDEM
12 | Project Admin | Bob Robertson | State of Florida | Budget Appropriation | MLK Intersection Improvements | 673619 | 317000 |  | 990619
13 | Project Admin | Nick Makris | Florida Department of Environmental Protection | Recreational Trails Program | For construction of the Elfers Spur Trail | 327979 | 900000 |  | 1227979 | POP Ends 10/09/25 | 1st reimbursement received/no further reimbursement until project completion
14 | Project Admin | Bob Robertson or P.J. Harbert | US Dept. Housing and Urban Development | Community Project Funding Grant | Craig Park/Spring Bayou Seawall and Sidewalk Repair and Resiliency Upgrade | 2000000 | 0 | 1819410 | 3819410 |  | Design complete
15 | Public Services | P.J. Harbert/Tommy Kiger | Florida Department of Environmental Protection | Florida Resilient Coastlines Program (FRCP) Resilience Planning Grant | For completion of a vulnerability assessment and action plan | 191168 |  |  | 191168 | Waiting on final two deliverables acceptance from FDEP/Extended to 12/30/25
16 | Building Development | Shannon Brewer | FL Dept. of Agriculture and Consumer Services | Managing Community Forests Grant | Tree Inventory/Management Plan/Tree Planting | 55000 | 55000 |  | 110000 | Phase 1 complete/Phase 2 in progress
17 | Public Works | Anthony (Tony) Mannello/Nick Makris | SWFWMD | Cooperative Funding Grant Program | For stormwater infrastructure improvement projects (Pent/Grosse Ave SW Project) | 1368416 | 2041309 | 1640536 | 5050261 | Ongoing. Expected completion on 12/25. Nick Makris (PA) handles reimbursements. | Dig Pond #2, Install utilities from Cypress St south to Tarpon A. and pave.
18 | Public Works | Brandon Crum/James Burke/P.J. Harbert | Pinellas County | CDBG | Replacement of Exercise Equipment | 35999.86 | 12000 |  | 47999.86 | Going to bid soon
19 | Public Services | Jamie Taylor/P.J. Harbert | Pinellas County | CDBG | Community Center Sign/Repaving of Parking Lot | 90000 | 10000 |  | 100000 | Project will be underway end of April 2025
| Total Current Grants |  |  |  |  | 13642494.52 | 4572634.14 | 3459946 | 21675074.66
APPLIED/WAITING ON NOTIFICATION
| City Department | Contact | Grant Agency | Grant Name | Purpose of the Grant | Max Grant Amount | City Match Required to Receive the Grant | ARPA Funded | Total Project Value | Application Due Date | Est. Date of Funding Availability
20 | Public Services | P.J. Harbert/Jamie Taylor | HUD/Pinellas County | CDBG | Gymnasium floor | 142895 | 25000 |  | 167895 | Pinellas County recommended for funding | 2025-10-01
21 | Public Services | Tommy Kiger | FDEP | Resilient Florida | Wastewater Treatment Plant Electrical Resilency | 2207000 | 2207000 |  | 4414000 | Applied 08/26/24 | Ranked 17/143 by FDEP and falls within $200 million funding threshold/waiting on final State budget
22 | Project Administration | P.J. Harbert | FDEM | HMGP Idalia | Sponge Docks Flooding Abatement | See amounts in Current Grants | See amounts in Current Grants |  | See amounts in Current Grants | Applied 05/23/24 | Pinellas County LMS Workgroup placed project in Top Tier for recommended funding purposes.
23 | Fire Department | P.J. Harbert/Luigi Bossiello | Firehouse Subs | Firehouse Subs Foundation Grant | Fire hoses and nozzles | 23606.28 |  |  | 23606.28 | Applied 04/03/25
24 | Fire Department | P.J. Harbert/Richard Walsh | FEMA | Assistance to Firefighters Grant | Brush Truck | 351758.18 | 35175.82 |  | 386934 | Applied 12/20/24
25 | Project Administration | P.J. Harbert/Anthony Mannello/Megan Araya | FDEP | Watershed Master Plan | Watershed Master Plan | 215461.5 | 71820.5 |  | 287282 | Applied 02/13/25
26 | Police Department | P.J. Harbert/Steve Gassen | FDOT | Highway Safety Concept Paper | Speeding/Aggressive Driving | 43426 |  |  | 43426 | Applied 01/29/25
27 | Cultural and Civic Services | Diane Wood | NEA | National Endowment for the Arts | Grants for Arts Project | 43067 | 43067 |  | 86134 | Applied 04/04/25
28 | Project Administration | P.J. Harbert | State of Florida | State Appropriations | Stormwater Projects | 1165005 | 475156 |  | 1640161 | Applied 01/23/25 | First round of Budget Chair negotiations
29 | Project Administration | P.J. Harbert | FDOT | Community Project Funding "Federal Appropriations" | Beckett Bridge | 4309755 | 257088 |  | 4566843 | Applied 04/07/25
30 | Fire Department | P.J. Harbert/Megan Araya | Sprouts Market | Hurricane Supplies | Hurricane Supplies |  |  |  |  | Applied 04/10/25
31 | Police Department | P.J. Harbert/Steve Gassen | FDOT | Highway Safety Concept Paper | DUI Enforcement | 30000 |  |  | 30000 | Applied 01/16/25
| Total Pending Grants |  |  |  |  | 8531973.96 | 3114307.32 | 0 | 11646281.28
FUTURE GRANTS
| City Department | Contact | Grant Agency | Grant Name | Purpose of the Grant | Max Grant Amount | City Match Required to Receive the Grant | ARPA Funded | Total Project Value | Application Due Date | Est. Date of Funding Availability
32 | Project Administration | P.J. Harbert | FDEM | HMGP | Disaster Recovery | [5 empty] | HMGP Helene: $240,228,219.35 HMGP Milton: $176,019,986.15
33 | Project Administration | P.J. Harbert | HUD | CDBG-DR | Disaster Recovery | [5 empty] | Total of $ 813,783,000 available/City amount to be determined/Pinellas County has not submitted Action Plan
34 | Public Works | P.J. Harbert/Marco Villagomez | Pinellas County | Municipal Recycling Grant | Reimbursement |  |  |  |  | Due 09/25
Total Future Grants/Sponsorships/Donations
TOTAL ALL GRANTS
[6 empty] | Grant Amount | City Match | ARPA | Total Project Value
| Current Grants |  |  |  |  | 13642795 | 4572634 | 3459946 | 21675375
| Applied For |  |  |  |  | 8531974 | 3114307 | 0 | 11646281
| Total All Grants |  |  |  |  | 22174769 | 7686941 | 3459946 | 33321656
[7 empty] | 76.93% |  | Grant Funded
PAST GRANTS
| City Department | Contact | Grant Agency | Grant Name | Purpose of the Grant | Grant Amount |  |  | Total Project Value |  | Closed
| Fire Department | Megan Araya | Publix | Publix Charities Giving | Hurricane Supplies | 150 |  |  | 150 |  | Yes
| Fire Department | Megan Araya | Walmart | Local Community Grants | Hurricane Supplies | 3144 |  |  | 3144 |  | Yes
| Cultural and Civic Services | Diane Wood | State of Florida, Division of Cultural Affairs | General Support Grant | Supports general program activities for local arts program | 50000 |  |  | 50000 |  | Yes
| Cultural and Civic Services | Denise Manning | Florida Humanities | Florida Talks | Library Speaker | 300 |  |  | 300 |  | Yes
| Cultural and Civic Services | Brandon Groc | National Endowment of the Arts | Arts Engagement |  | 10000 |  |  | 20000 |  | Yes
| Cultural Services and Economic Development | Diane Wood | Creative Pinellas | Arts and Economic Prosperity |  | 1200 |  |  | 2400 |  | Yes
| Planning and Zoning | Caroline Lanford | Florida Department of State | Small Matching Grant | Historic District and Greektown Survey Update | 50000 |  |  | 50000 |  | Yes
| Planning and Zoning | Caroline Lanford | Florida Department of State | Small Matching Grant | Historic District and Greektown Survey Update | 50000 |  |  | 50000 | Final documents and reimbursement requests have been submitted to the State.
| Planning and Zoning | Renea Vincent | National Trust for Historic Preservgation | Africa American Cultural Heritage Action Fund | Cultural Resources Survey for Union Academy neighborhood | 25000 |  |  | 50000 |  | Yes
| Police Department | Frank Ruggiero | Dept. of Justice | Bulletproof Vests 2021 | Equipment Purchae | 6185 |  |  | 12371 |  | Yes
| Police Department | Frank Ruggiero | Dept. of Justice | Bulletproof Vests 2022 | Equipment Purchae | 3555 |  |  | 7310 |  | Yes
| Police Department | Frank Ruggiero | State of Florida | JAG | Youth Education Classes | 4283 |  |  | 4283 |  | Yes
| Police Department | Frank Ruggiero | State of Florida | JAG | Defibrillators | 4314 |  |  | 4314 |  | Yes
| Police Department | Frank Ruggiero | IPTM | DRE Callout | DRE Callout Reimbursement | 3000 |  |  | 3000 |  | Yes
| Police Department | Frank Ruggiero | State of Florida | JAG | 3D Scanner | 40873 |  |  | 40873 |  | Yes
| Public Services | Tom Kiger | SWFWMD | Cooperative Funding Grant | FY22 Water Conservation | 15000 |  |  | 30000 |  | Yes
| Project Administration | Bob Robertson | FDOT | Highway Safety Grant | Tarpon/Huey | 314830 |  |  | 1264830 |  | Yes
| Public Works | Marco Villagomez | Pinellas County | Municipal Recycling Grant | Recycling Reimbursment | 18495 |  |  | 18495 |  | Yes
| Public Works | Paul Hopkins | TBRPC | TBRPC | Vehicle Wraps
| Fire Department | Richard Walsh | ACG Foundation | Traffic Safety Grant | Cones/Speed Bumps | 4274.4 |  |  | 4274.4 | Awarded 07/12/24 | Final report due 04/2025
| Fire Department | Richard Walsh | Florida State Fire Marshal | Florida Firefighter Cancer Decontamination Grant | PPE |  |  |  |  | Awarded | Reimbursement needs submitted
| Building Development | Shannon Brewer | USDA | Urban and Community Forestry | Tree Canopies | 100000 | 100000 |  | 200000 | Federal government pulled funding. Grant closed.
| Cultural and Civic Services | Denise Manning | Florida Humanities | Florida Talks | Speaker | 300 | 0 | 0 | 300 | Awarded
Note on K8: Paige Tillison: 11/2022 - Grant Received

## Grant Log
GRANT LOG
Grant Number | Offical Grant Name | Grant Amount | Complete
LP52028 | Tarpon Springs Anclote River Dredge Project
LPA0394 | Tarpon Springs Mango Street Safety and Drainage Improvements
LPA0395 | Tarpon Springs MLK/South Spring Blvd. Flooding Abatement & Intersection Safety Improvements |  | X
LPA0229 | Tarpon Springs Sponge Docks Flooding Abatement | 1,738,390 (State App. Funding)
24-PLC-16 | Public Library Construction Grant Project | 500000
T2102 | Elfers Spur Trail Project | 327979
B-23-CP-FL-0363 | Craig Park/Spring Bayou Seawall and Sidewalk Repair and Resiliency Upgrade | 2000000